## User Story Backlog
Iteration | Story Points | Title | As a/an | I want to… | so that I can…
I1 | 3 | Ability to Login | Customer/Admin | log in to the application | get a peronalised experience
I1 | 3 | Ability to sign out | Customer/Admin | sign out from the application | protect my personal information from being used by others.
I1 | 3 | Ability to search for restaurants | Customer/Admin | search restaurants by their names | quickly find the restaurant from which I want to order
I1 | 3 | Ability to view restaurant menus | Customer/Admin | look at menus of restaurants | select which dish(es) to order
I2 | 5 | Ability to add menu items to cart | Customer/Admin | add selected food items to my cart | finalize my order
I2 | 2 | Ability to remove menu items from cart | Customer/Admin | remove unwanted items from my cart | discard any items I don't want to order
I2 | 5 | Ability to place an order with the restaurant | Customer/Admin | place an order with the restaurant | get the food I ordered
I2 | 5 | Ability to view order history | Customer/Admin | view the history of my orders | view my previous selections incase I want to refer and re-order something I liked
I2 | 3 | Ability to enter payment information | Customer/Admin | enter my payment details | pay for my order to the restaurant
I2 | 5 | Ability to receive/view order information from customers | Restaurant/Partners | view orders placed by customers | accept or reject the orders
I2 | 5 | Ability to add details of a new restaurant and its menu | Admin | add restaurant details to the website | make the restaurant available for customers to order from