## Sheet1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 01. Account Management | 1.01 | Account Management | Create API structure | 2022-10-01 | 2022-10-01 | 75% | Nikita Jarile
2 | 01. Account Management | 1.01 | Account Management | Implement core functionality | 2022-10-02 | 2022-10-04 | 75% | Nikita Jarile
3 | 01. Account Management | 1.01 | Account Management | Implement GUI | 2022-10-05 | 2022-10-07 | 75% | Nikita Jarile
4 | 01. Account Management | 1.01 | Account Management | Setup access for users and admins | 2022-10-08 | 2022-10-08 | 75% | Nikita Jarile
5 | 01. Account Management | 1.01 | Account Management | Implement validations | 2022-10-08 | 2022-10-08 | 75% | Nikita Jarile
6 | 01. Account Management | 1.01 | Account Management | Enable and implement logs | 2022-10-09 | 2022-10-09 | 75% | Nikita Jarile
7 | 01. Account Management | 1.01 | Account Management | Develop test cases | 2022-10-01 | 2022-10-05 | 75% | Sen Wang
8 | 01. Account Management | 1.01 | Account Management | Test functionality | 2022-10-09 | 2022-10-12 | 75% | Sen Wang
9 | 01. Account Management | 1.02 | Account Summary | Implement core functionality | 2022-10-01 | 2022-10-05 | 75% | Sanket Koli
10 | 01. Account Management | 1.02 | Account Summary | Implement GUI | 2022-10-06 | 2022-10-08 | 75% | Sanket Koli
12 | 01. Account Management | 1.02 | Account Summary | Implement validations | 2022-10-09 | 2022-10-09 | 75% | Sanket Koli
13 | 01. Account Management | 1.02 | Account Summary | Enable and implement logs | 2022-10-10 | 2022-10-10 | 75% | Sanket Koli
14 | 01. Account Management | 1.02 | Account Summary | Develop test cases | 2022-10-06 | 2022-10-07 | 75% | Divya Kotapati
15 | 01. Account Management | 1.02 | Account Summary | Test functionality | 2022-10-12 | 2022-10-15 | 75% | Divya Kotapati
16 | 06. Database development | 6.01 | Table creation | Create db scripts for tables creation | 2022-10-01 | 2022-10-03 | 100% | Avni Mitawalkar
17 | 06. Database development | 6.01 | Table creation | Run and test scripts on db | 2022-10-03 | 2022-10-03 | 100% | Avni Mitawalkar