## User Story Backlog
Iteration | Module | Title | As a/an | I want to… | so that I can… | Story Points | Story Constraints | Exceptions | Extensions
I1 | 01. Account Management | 01.01 Account Management | Sales broker, Accountant, Customer care representative, Supervisor, Subscribed Customer, Partner Restaurant | log in to my account in the application | get a peronalised experience | 5 | Users should be able to create accounts and login to the application using their credentials. | User must complete the registration process in one go. Progress cannot be saved. User should enter correct username and password | A functionality of resetting password in case old password is forgotten can be added.
I1 |  | 01.02 Account Summary | Accountant, Customer care representative, Supervisor, Subscribed Customer, Partner Restaurant | get an overview of my account | set my personal preferences and store my personal information in the application | 3 | Users should be able to set and view their personal details and preferences pertaining to the application. | User must setup all required information. | User order preference can be calculated and displayed based on order history.