## Road Map
Nutrameals
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/14/22 | Iteration 2 - 11/04/22 | Iteration 3 - 11/18/22 | Iteration 4 - 12/16/22
Module 1 - Account Management | 01.01 Account Management | 5 | X
| 01.02 Account Summary | 3 | X
| 01.03 User Support | 3 |  |  |  | X
Module 2 - Search | 02.01 Search Restaurant | 5 |  | X
| 02.02 Search for food items | 5 |  | X
Module 3 - Advertisement | 03.01 Post Advertisement | 3 |  |  |  | X
| 03.02 Post Modification | 3
| 03.03 Remove Advertisement | 3
Module 4 - Place Order | 04.01 Order Management | 5 |  |  | X
| 04.02 Order Track | 3
| 04.03 Order History | 5 |  |  | X
Module 5 - Payment Management | 05.01 Payment Validation | 3
| 05.02 Payment Method | 3 | 3
|  | VELOCITY: | 8 | 10 | 10 | 6

## Story Map
Epics |  | Nutrameals - User Story Map
Epic 1 - Account Management |  | Epic 1 - Account Management | Epic 2 - Search | Epic 3 - Advertisement | Epic 4 - Place Order | Epic 5 - Payment Management
Epic 2 - Search | User Stories | 01.01 Account Management
Epic 3 - Advertisement |  | 01.02 Account Summary |  |  |  |  | Iteration 1
Epic 4 - Place Order |  |  | 02.01 Search Restaurant
|  |  | 02.02 Search for food items |  |  |  | Iteration 2
04.01 Order Management
[5 empty] | 04.03 Order History |  | Iteration 3
01.03 User Support
|  |  |  | 03.01 Post Ad |  |  | Iteration 4